## Sheet1
Team 4 - Andrea, Christian, Emmy & Weiqing
Availability
|  | Goals | Andrea | Christian | Emmy | Weiqing
Sunday | 2019-12-08 | Initial list of technical & fundamental indicators | all day |  | all day
Monday | 2019-12-09 | Obtain data. If we all have access, we can already start writing code. Based on the size of the data, we may look into using AWS to store and run code.
Tuesday | 2019-12-10 | complete code for unsupervised learning on both sets of data, run tests on small portions of the data set to begin training. | CLASS
Wednesday | 2019-12-11 | Code to test different models |  |  | after 5
Thursday | 2019-12-12 | Complete testing and actually run code for all stocks. This may take a while. | CLASS
Friday | 2019-12-13 |  |  |  | after 5
Saturday | 2019-12-14 | If we are in good shape, lets attempt part 3 where we write algorithms to execute trades and backtest strategies. | CLASS
Sunday | 2019-12-15 |  |  |  | all day
Monday | 2019-12-16 |  | after 7
Tuesday | 2019-12-17 | Presentation materials & visualizations mostly complete | CLASS
Wednesday | 2019-12-18 |  | after 7 |  | after 5
Thursday | 2019-12-19 | Rehearsing Pitch & Finalizing Materials | CLASS
Friday | 2019-12-20 |  | after 7 |  | after 5
Saturday | 2019-12-21 | --- | PRESENTATION DAY
notes |  |  | note: I can meet anyday from week class at 530 and can stay late.. Also Saturday 14th after class